Aaron Jencks
Collin Fischels

Project Charter

Project Name: Red Pitaya
Project Manager: Aaron Jencks
Sponsor: Steve Long
Customer: Rockwell Collins
Start Date: 1/19/2018 End Date: 5/8/2018
Budget: $500
Known Constraints:
- Team of 3 people
- Must be done by the end of the semester
- Must not exceed the allocated budget
Project Goal: Create a software defined radio using the kit provided, and integrated with software. It will be able to receive and transmit signals via an antenna attached to the hardware. Look into using it as a piece of test equipment (using it as an oscilloscope, spectrum analyzer, etc...)
Requirements/Scope:
The hardware will be responsible for:
- Communicating with the antenna
- Filtering input to the correct frequency and amplifying it to a detectable voltage level
- Transmitting data via the antenna using the output from the software
The software will be responsible for:
- Automatic Gain Control (AGC)
- Retrieving the intelligence from the Waveform
- Amplifying the intelligence to an audible volume
- Determining if there is data that needs to be transmitted, via either an analog input, or a serial/parallel input port.
  - This implies that the software will also be responsible to generating the correct AM/FM waveform for the corresponding data being input.
    The project is considered complete when the team can demonstrate a working software controlled radio to the customer.

Milestones/Deliverables:
- Completing the charter
- Obtaining the SDR
- Getting the SDR to work:
  - Prove that the SDR can be connected to the computer
  - Prove that the SDR can be coded, with a simple tutorial
  - Prove that the SDR can transmit radio signals
  - Prove that the SDR can receive radio signals
- Present the working final product to the customer/sponsor
Risks:
- The SDR does not work upon reception (12%)
  - Must spend time getting a second one
- Programming the SDR takes longer than expected (75%)
  - Must spend extra time getting software to work.
Team:
Aaron Jencks (Project Manager)
Collin Fischels (CO-Project Manager)
Jacob (Third Wheel)